## DefectList
Defect ID | Title | Screen | Steps | Exepect Result | Actual Result | Propose | Priority | Serveriry | Date | Owner | TC'ID | Assign To | Build | System | Evident
DE_01 | Can't return to previous page | Screen Add Tests & Quizzes | S1: Log in to the Myworkspace website S2: Go to the tests & quizzes screen S3: Click "Add" S4: Return to the previous screen | S3: The "Add Assessments" screen appears. S4: Can return to the previous screen | S3: The "Add Assessments" screen appears. S4: Cann't return to the previous screen. Notice requesting form submission |  | LOW | MEDIUM | 2024-04-12 | LUAN |  | LUAN | Buil1.0 | Win 10 2023
DE_02 | Unable to determine file type | Screen Add Tests & Quizzes | S1: Log in to the Myworkspace website S2: Go to the tests & quizzes screen S3: Click "Add" S4: Select question type S5: Click button "Add Attachments" S6: Insert the link (.zip,rar) | S6: Cannot be included | S6: Can be put in |  | LOW | MEDIUM | 2024-04-12 | LUAN |  | LUAN | Buil1.0 | Win 10 2023
DE_03 | Include 2 images in 1 question | Screen Add Tests & Quizzes | S1: Log in to the Myworkspace website S2: Go to the tests & quizzes screen S3: Click "Add" S4: Select question type S5: Click button "Add Attachments" S6: Insert the link to the 2 images | S6: Cannot upload 2 images at the same time | S6: Can be put in |  | LOW | MEDIUM | 2024-04-12 | LUAN |  | LUAN | Buil1.0 | Win 10 2023
DE_04 | Include 2 recordings in 1 question | Screen Add Tests & Quizzes | S1: Log in to the Myworkspace website S2: Go to the tests & quizzes screen S3: Click "Add" S4: Select question type S5: Click button "Add Attachments" S6: Insert the link to the 2 recordings | S6: Cannot upload 2 recordings at the same time | S6: Can be put in |  | LOW | MEDIUM | 2024-04-12 | LUAN |  | LUAN | Buil1.0 | Win 10 2023
DE_05 | Do not automatically shorten the link when it is too long | Screen Add Tests & Quizzes | S1: Log in to the Myworkspace website S2: Go to the tests & quizzes screen S3: Click "Add" S4: Select question type S5: Click button "Add Attachments" S6:Provide a link with a path consisting of many characterss | S6: Automatically shorten the link to go to | S6: Cannot be inserted and the message:"The name"..."is too long" appears. |  | LOW | MEDIUM | 2024-04-12 | LUAN |  | LUAN | Buil1.0 | Win 10 2023
DE_06 | When you click show page in the "Select from resources" section, you will f5 the page again | Screen Add Tests & Quizzes | S1: Log in to the Myworkspace website S2: Go to the tests & quizzes screen S3: Click "Add" S4: Select question type S5: Click button "Add Attachments" S6:Click"Select from resources" S7: Show other sites Show other sites | S7: Display other site | S7: Do not restart the website |  | LOW | MEDIUM | 2024-04-12 | LUAN |  | LUAN | Buil1.0 | Win 10 2023
DE_07 | Uneven interface on mobile | Screen Add Tests & Quizzes | S1: Log in to the Myworkspace website S2: Go to the tests & quizzes screen | S2: Display the table of contents to select the function to perform | S2: Uneven arrangement between cells |  | LOW | MEDIUM | 2024-04-12 | LUAN |  | LUAN | Buil1.0 | Win 10 2023
DE_08 | Error Adding photos on mobile | Screen Add Tests & Quizzes | S1: Log in to the Myworkspace website S2: Go to the tests & quizzes screen S3: Click "Add" S4: Select question type S5: Click button "Add Attachments" S6: Insert the 1 images on mobile | S6: Photo added successfully | S6: Cannot add |  | LOW | MEDIUM | 2024-04-12 | LUAN |  | LUAN | Buil1.0 | Win 10 2023
DE_09 | Should change the font color in important places | Screen Add Tests & Quizzes | S1: Log in to the Myworkspace website S2: Go to the tests & quizzes screen S3: Click "Add" S4: Select question type | S4: In important places, make the text red or darker | S4: The letters are the same color |  | LOW | MEDIUM | 2024-04-12 | LUAN |  | LUAN | Buil1.0 | Win 10 2023
DE_10 | No need for right or wrong results, still run the question | Screen Add Tests & Quizzes | S1: Log in to the Myworkspace website S2: Go to the tests & quizzes screen S3: Click "Add" S4: Select question type S5: Enter Question Text S6: Press "Create" | S6: Ask for correct or incorrect results | S6:Run as long as you have the "answer key" |  | LOW | MEDIUM | 2024-04-12 | LUAN |  | LUAN | Buil1.0 | Win 10 2023